## Sample SD-09 Sched
Cost Estimating Schedule Milestones
[27 empty] | Estimating Milestone | [14 empty] | Construction Milestones
Row | Cost Estimator | Cost Estimator Request | ADE | Project Manager | Project Engineer | Design Estimator | Construction Contractor | Bundle ID | Post Estimate | PMO ID | Order | Multiple Order | MAT | Project Name | Work Stream | Work Type | Engr Plan Year | Const Plan Year | Commitment Date | Station | Line | MP1 | MP2 | MI/ft/Ct | City | County | Class 5 | Class 4 | Class 3 | Class 2 | Negotiate Price | JE Ready to Route | JE Approved | Estimate Analysis | 30% Design Review Meeting | 30% Design Available | 60% Design Review Meeting | 60% Design Available | 90% Design Review Meeting | 90% Design Available | IFC | NTP | MOB | Tie-In | ENRO | Unit Capture | Notes | Edit
1 | Sauer, Shauns | Assigned | Brown, Michael | Walker, Brian | Eng, 1 |  | Contractor 1 | PB-1111 |  | A-1111 | 740000001 | No | H12 | A Project name with information 1 | In-Line Inspection | In-Line Inspection | 2024 | 2025 | 2025-12-31 | Station Name | L-200 | 125.25 | 126.25 |  | A City 1 | County 1 | 2025-01-01 |  | 2025-02-01 | 2025-03-07 | 2025-04-01 | 2025-03-10 | 2025-05-01 |  |  | 2024-11-01 | 2025-11-10 | 11/31/2025 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
2 | Simther, Joe | Assigned | Black, Danie | Robinson, Stephanie | Eng, 2 |  | Contractor 2 | PB-1112 |  | A-1235 | 740000002 | No | 751 | A Project name with information 2 | Assest Engineering | Assest Engineering | 2024 | 2025 | 2025-12-31 |  | L-300B | 125.25 | 126.25 |  | A City 2 | County 2 | 2025-01-02 |  | 2025-02-02 | 2025-03-10 | 2025-04-02 | 2025-03-11 | 2025-05-02 |  |  | 2024-11-02 | 2025-11-11 | 2026-12-01 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
3 | Simth, John | Assigned | Silver, Robert | King, Jason | Eng, 3 |  | Contractor 3 | PB-1113 |  | A-1236 | 740000003 | No | H13 | A Project name with information 3 | Replacement | Replacement | 2024 | 2025 | 2025-12-31 | Station Name | L-164 | 125.25 | 126.25 |  | A City 3 | County 3 | 2025-01-03 |  | 2025-02-03 | 2025-03-11 | 2025-04-03 | 2025-03-12 | 2025-05-03 |  |  | 2024-11-03 | 2025-11-12 | 11/31/2027 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
4 | Simth, John | Assigned | Silver, Robert | King, Jason | Eng, 4 |  | Contractor 4 | PB-1114 |  | T-1234 | 740000004 | No | 752 | A Project name with information 4 | Replacement | Replacement | 2024 | 2025 | 2025-12-31 |  | L-400 | 125.25 | 126.25 |  | A City 4 | County 4 | 2025-01-04 |  | 2025-02-04 | 2025-03-12 | 2025-04-04 | 2025-03-13 | 2025-05-04 |  |  | 2024-11-04 | 2025-11-13 | 11/31/2028 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
5 | Simth, John | Assigned | Silver, Robert | King, Jason | Eng, 5 |  | Contractor 5 |  |  | T-1235 | 740000005 | No | H14 | A Project name with information 5 | Replacement | Replacement | 2024 | 2025 | 2025-12-31 |  | L-300A | 125.25 | 126.25 |  | A City 5 | County 5 | 2025-01-05 |  | 2025-02-05 | 2025-03-13 | 2025-04-05 | 2025-03-14 | 2025-05-05 |  |  | 2024-11-05 | 2025-11-14 | 11/31/2029 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
6 | Anderson, Thomas | Assigned | Paul Smith | Young, Alexander | Some Name 4 |  | Contractor 7 |  |  | T-1236 | 740000006 | No | 753 | A Project name with information 6 | Replacement | Replacement | 2024 | 2025 | 2025-01-06 |  | L-201 | 125.25 | 126.25 |  | A City 6 | County 6 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
7 | Anderson, Thomas | Assigned | Joe Smith | Young, Alexander | Some Name 1 |  | Contractor 7 |  |  | T-1237 | 740000007 | No | H15 | A Project name with information 7 | Replacement | Station | 2024 | 2025 |  |  | L-300B | 125.25 | 126.25 |  | A City 7 | County 7 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
8 | Anderson, Thomas |  | Paul Smith | Young, Alexander | Some Name 4 |  | Contractor 7 |  |  | C-1234 | 840000001 | No | 754 | A Project name with information 8 | Station | Strength Test | 2024 | 2025 | 2025-01-08 | Staion Name | L-636 | 125.25 | 126.25 |  | A City 8 | County 8 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
9 | Anderson, Thomas | Assigned | Paul Smith | A name 4 | Some Name 1 |  | Contractor 4 | PB-1111 |  | C-1235 | 840000002 | No | H16 | A Project name with information 9 | Strength Test | Corrosion | 2024 | 2025 | 2025-01-09 | Staion Name | L-872 | 125.25 | 126.25 |  | A City 9 | County 9 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
10 | Anderson, Thomas | Assigned | Joe Smith | A name 5 | Some Name 1 |  | Contractor 7 | PB-1112 |  | C-1236 | 840000003 | No | 755 | A Project name with information 10 | Corrosion | Digs | 2024 | 2025 | 2025-01-10 | Staion Name | L-300A | 125.25 | 126.25 |  | A City 10 | County 10 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
11 | Anderson, Thomas |  | Joe Smith | A name 4 |  | Someones Name | Contractor 4 | PB-1113 |  | C-1237 | 840000004 | No | H17 | A Project name with information 11 | Digs | In-Line Inspection | 2024 | 2025 | 2025-01-11 | Staion Name | L-202 | 125.25 | 126.25 |  | A City 11 | County 11 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
12 | Anderson, Thomas |  | Joe Smith | A name 4 |  | Someones Name | Contractor 2 | PB-1114 |  | C-1238 | 840000005 | No | 756 | A Project name with information 12 | In-Line Inspection | Assest Engineering | 2024 | 2025 | 2025-01-12 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 12 | County 12 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
13 | Jane Smith |  | Joe Smith | A name 5 | Some Name 1 | Someones Name | TBD | PB-1115 |  | R-1234 | 840000006 | No | H18 | A Project name with information 13 | Assest Engineering | Replacement | 2024 | 2025 | 2025-01-13 | Staion Name | L-1108 | 125.25 | 126.25 |  | A City 13 | County 13 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
14 | Jane Smith | Assigned | Janney Red | A name 4 |  | Someones Name | Contractor 2 | PB-1116 |  | R-1235 | 840000007 | No | 757 | A Project name with information 14 | Replacement | Replacement | 2024 | 2025 | 2025-01-14 | Staion Name | L-1344 | 125.25 | 126.25 |  | A City 14 | County 14 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
15 | Jane Smith |  | Paul Smith | A name 4 |  |  | TBD | PB-1117 |  | R-1236 | 840000008 | No | H19 | A Project name with information 15 | Replacement | Replacement | 2024 | 2025 | 2025-01-15 | Staion Name | L-300A | 125.25 | 126.25 |  | A City 15 | County 15 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
16 | Jane Smith | Assigned | Joe Smith | A name 3 | Some Name 1 |  | Contractor 2 | PB-1118 |  | R-1237 | 840000009 | No | 758 | A Project name with information 16 | Replacement | Replacement | 2024 | 2025 | 2025-01-16 | Staion Name | L-203 | 125.25 | 126.25 |  | A City 16 | County 16 | 2025-10-02 |  | 2025-11-01 |  | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
17 | Jane Smith |  | Janney Red | A name 3 | Some Name 5 |  | Contractor 2 | PB-1119 |  | D-1234 | 840000010 | No | H20 | A Project name with information 17 | Replacement | Replacement | 2024 | 2025 |  | Staion Name | L-300B | 125.25 | 126.25 |  | A City 17 | County 17 | 2025-10-02 |  |  | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
18 | Shaun Sauer |  | Brown, Michael | A name 3 | Some Name 5 |  | TBD | PB-1120 |  | D-1235 | 740000006 | No | 759 | A Project name with information 18 | Replacement | Station | 2024 | 2025 | 2025-01-18 | Staion Name | L-1580 | 125.25 | 126.25 |  | A City 18 | County 18 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 |  | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
19 | Shaun Sauer | Assigned | Brown, Michael | A name 3 | Some Name 5 |  | Contractor 2 | PB-1121 |  | D-1236 | 740000008 | No | H21 | A Project name with information 19 | Station | Replacement | 2024 | 2025 | 2025-01-19 | Staion Name | L-1816 | 125.25 | 126.25 |  | A City 19 | County 19 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 |  |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
20 | Shaun Sauer |  | Brown, Michael | A Name 2 | Some Name 2 |  | Contractor 2 | PB-1122 |  | D-1237 | 740000009 | No | 760 | A Project name with information 20 | Strength Test | Replacement | 2024 | 2025 | 2025-01-20 | Staion Name | L-300A | 125.25 | 126.25 |  | A City 20 | County 20 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
21 | Shaun Sauer |  | Brown, Michael | A Name 2 | Some Name 2 |  | Contractor 3 | PB-1123 |  | D-1234A | 740000010 | No | H22 | A Project name with information 21 | Corrosion | Station | 2024 | 2025 | 2025-01-21 | Staion Name | L-204 | 125.25 | 126.25 |  | A City 21 | County 21 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
22 | Shaun Sauer |  | Brown, Michael | A Name 2 | Some Name 2 |  | Contractor 3 | PB-1124 |  | D-1234B | 740000011 | Yes | 761 | A Project name with information 22 | Digs | Strength Test | 2024 | 2025 | 2025-01-22 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 22 | County 22 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 |  | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
23 | Shaun Sauer | Assigned | Brown, Michael | A name 4 | Some Name 2 |  | Contractor 7 | PB-1125 |  | D-1234C | 740000012 | Yes | H23 | A Project name with information 23 | Replacement | Replacement | 2024 | 2025 | 2025-01-23 | Staion Name | L-2052 | 125.25 | 126.25 |  | A City 23 | County 23 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
24 | Shaun Sauer | Assigned | Brown, Michael | A name 4 | Some Name 2 |  | Contractor 7 | PB-1126 |  | D-1234D | 740000013 | Yes | 762 | A Project name with information 24 | Replacement | Replacement | 2025 | 2026 | 2025-01-24 | Staion Name | L-2288 | 125.25 | 126.25 |  | A City 24 | County 24 | 2025-10-02 |  |  | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
25 | Shaun Sauer | Assigned | Brown, Michael | A name 4 | Some Name 2 |  | TBD |  |  | S-1234 | 740000014 | Yes | H24 | A Project name with information 25 | Station | Station | 2026 | 2027 | 2025-01-25 | Staion Name | L-300A | 125.25 | 126.25 |  | A City 25 | County 25 | 2025-10-02 |  | 2025-11-01 |  | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
26 | Anderson, Thomas | Assigned | Paul Smith | A name 3 | Some Name 1 |  | Contractor 2 |  |  | A-1237 | 740000015 | No | H13 | A Project name with information 26 | Replacement | Replacement | 2024 | 2025 |  | Staion Name | L-2052 | 125.25 | 126.25 |  | A City 26 | County 26 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 |  | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
27 | Shaun Sauer | Assigned | Brown, Michael | A name 1 | Some Name 2 |  | Contractor 4 |  |  | A-1238 | 740000016 | Yes | 752 | A Project name with information 27 | Replacement | Station | 2024 | 2025 | 2025-01-27 | Staion Name | L-2288 | 125.25 | 126.25 |  | A City 27 | County 27 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
28 | Anderson, Thomas | Assigned | Janney Red | A name 4 | Some Name 3 |  | Contractor 2 |  |  | A-1239 | 740000017 | Yes | H14 | A Project name with information 28 | Station | Replacement | 2025 | 2025 | 2025-01-28 | Staion Name | L-300A | 125.25 | 126.25 |  | A City 28 | County 28 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 |  | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
29 | Shaun Sauer | Assigned | Brown, Michael | A name 4 | Some Name 4 |  | TBD |  |  | T-1238 | 740000018 | No | 753 | A Project name with information 29 | Strength Test | Replacement | 2026 | 2025 | 2025-01-29 | Staion Name | L-205 | 125.25 | 126.25 |  | A City 29 | County 29 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  |  | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
30 | Anderson, Thomas | Assigned | Joe Smith | A name 4 | Some Name 5 |  | TBD |  |  | T-1239 | 740000019 | Yes | H15 | A Project name with information 30 | Corrosion | Station | 2026 | 2025 | 2025-01-30 | Staion Name | L-201 | 125.25 | 126.25 |  | A City 30 | County 30 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
31 | Anderson, Thomas |  | Paul Smith | A name 5 | Some Name 2 |  | TBD |  |  | D-1234B | 740000020 | No | H14 | A Project name with information 31 | Replacement | Replacement | 2024 | 2025 | 2025-01-31 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 31 | County 31 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  |  | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
32 | Anderson, Thomas |  | Paul Smith | A name 4 | Some Name 2 |  | Contractor 2 |  |  | D-1234C | 740000021 | No | 753 | A Project name with information 32 | Station | Station | 2025 | 2025 | 2025-02-01 | Staion Name | L-636 | 125.25 | 126.25 |  | A City 32 | County 32 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
33 | Anderson, Thomas |  | Joe Smith | A name 5 | Some Name 2 |  | Contractor 2 |  |  | D-1234D | 740000022 | No | H15 | A Project name with information 33 | Strength Test | Strength Test | 2026 | 2025 | 2025-02-02 | Staion Name | L-872 | 125.25 | 126.25 |  | A City 33 | County 33 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 |  |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
34 | Anderson, Thomas | Assigned | Joe Smith | A name 4 | Some Name 1 |  | Contractor 3 |  |  | S-1235 | 740000023 | No | 754 | A Project name with information 34 | Corrosion | Corrosion | 2024 | 2025 | 2025-02-03 | Staion Name | L-300A | 125.25 | 126.25 |  | A City 34 | County 34 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
35 | Anderson, Thomas | Assigned | Joe Smith | A name 4 | Some Name 2 |  | Contractor 3 |  |  | A-1240 | 740000024 | Yes | H16 | A Project name with information 35 | Digs | Digs | 2025 | 2025 | 2025-02-04 | Staion Name | L-202 | 125.25 | 126.25 |  | A City 35 | County 35 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
36 | Anderson, Thomas | Assigned | Joe Smith | A name 5 | Some Name 3 |  | Contractor 7 |  |  | A-1241 | 740000025 | Yes | H15 | A Project name with information 36 | In-Line Inspection | In-Line Inspection | 2026 | 2025 | 2025-02-05 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 36 | County 36 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
37 | Anderson, Thomas | Assigned | Janney Red | A name 4 | Some Name 4 |  | Contractor 7 |  |  | A-1242 | 740000026 | Yes | 754 | A Project name with information 37 | Assest Engineering | Assest Engineering | 2024 | 2025 | 2025-02-06 | Staion Name | L-1108 | 125.25 | 126.25 |  | A City 37 | County 37 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
38 | Anderson, Thomas | Assigned | Paul Smith | A name 4 | Some Name 5 |  | TBD |  |  | T-1240 | 740000027 | Yes | H16 | A Project name with information 38 | Replacement | Replacement | 2025 | 2025 | 2025-02-07 | Staion Name | L-1344 | 125.25 | 126.25 |  | A City 38 | County 38 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
39 | Anderson, Thomas | Assigned | Joe Smith | A name 3 | Some Name 2 |  | Contractor 2 |  |  | T-1241 | 740000028 | No | 755 | A Project name with information 39 | Replacement | Replacement | 2026 | 2025 | 2025-02-08 | Staion Name | L-300A | 125.25 | 126.25 |  | A City 39 | County 39 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
40 | Jane Smith | Assigned | Janney Red | A name 3 | Some Name 2 |  | Contractor 4 |  |  | D-1234B | 740000029 | Yes | H17 | A Project name with information 40 | Replacement | Replacement | 2024 | 2025 |  | Staion Name | L-203 | 125.25 | 126.25 |  | A City 40 | County 40 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
41 | Jane Smith | Assigned | Paul Smith | A name 3 | Some Name 2 |  | Contractor 2 |  |  | D-1234C | 740000030 | Yes | H16 | A Project name with information 41 | Replacement | Replacement | 2025 | 2025 | 2025-02-10 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 41 | County 41 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
42 | Jane Smith | Assigned | Paul Smith | A name 4 | Some Name 3 |  | Contractor 3 |  |  | D-1234C | 740000031 | Yes | H17 | A Project name with information 42 | Replacement | Replacement | 2025 | 2025 | 2025-02-11 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 42 | County 42 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
43 | Jane Smith | Assigned | Joe Smith | A name 3 | Some Name 2 |  | Contractor 2 |  |  | T-1242 | 740000032 | No | 756 | A Project name with information 43 | Replacement | Replacement | 2024.5 | 2025 | 2025-02-12 | Staion Name | L-300A | 125.25 | 126.25 |  | A City 43 | County 43 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
44 | Jane Smith | Assigned | Janney Red | A name 3 | Some Name 2 |  | Contractor 4 |  |  | D-1234B | 740000033 | Yes | H17 | A Project name with information 44 | Replacement | Replacement | 2024.3 | 2025 |  | Staion Name | L-204 | 125.25 | 126.25 |  | A City 44 | County 44 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
45 | Jane Smith | Assigned | Paul Smith | A name 3 | Some Name 2 |  | Contractor 2 |  |  | D-1234C | 740000034 | Yes | H16 | A Project name with information 45 | Replacement | Replacement | 2024.1 | 2025 | 2025-02-14 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 45 | County 45 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
46 | Jane Smith | Assigned | Paul Smith | A name 4 | Some Name 3 |  | Contractor 3 |  |  | D-1234C | 740000035 | Yes | H17 | A Project name with information 46 | Replacement | Replacement | 2023.9 | 2025 | 2025-02-15 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 46 | County 46 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
47 | Jane Smith | Assigned | Joe Smith | A name 3 | Some Name 2 |  | Contractor 2 |  |  | T-1243 | 740000036 | No | 757 | A Project name with information 47 | Replacement | Replacement | 2023.7 | 2025 | 2025-02-16 | Staion Name | L-300A | 125.25 | 126.25 |  | A City 47 | County 47 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
48 | Jane Smith | Assigned | Janney Red | A name 3 | Some Name 2 |  | Contractor 4 |  |  | D-1234B | 740000037 | Yes | H17 | A Project name with information 48 | Replacement | Replacement | 2023.5 | 2025 |  | Staion Name | L-205 | 125.25 | 126.25 |  | A City 48 | County 48 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
49 | Jane Smith | Assigned | Paul Smith | A name 3 | Some Name 2 |  | Contractor 2 |  |  | D-1234C | 740000038 | Yes | H16 | A Project name with information 49 | Replacement | Replacement | 2023.3 | 2025 | 2025-02-18 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 49 | County 49 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
50 | Jane Smith | Assigned | Paul Smith | A name 4 | Some Name 3 |  | Contractor 3 |  |  | D-1234C | 740000039 | Yes | H17 | A Project name with information 50 | Replacement | Replacement | 2023.1 | 2025 | 2025-02-19 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 50 | County 50 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
51 | Jane Smith | Assigned | Joe Smith | A name 3 | Some Name 2 |  | Contractor 2 |  |  | T-1244 | 740000040 | No | 758 | A Project name with information 51 | Replacement | Replacement | 2022.9 | 2025 | 2025-02-20 | Staion Name | L-300A | 125.25 | 126.25 |  | A City 51 | County 51 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
52 | Jane Smith | Assigned | Janney Red | A name 3 | Some Name 2 |  | Contractor 4 |  |  | D-1234B | 740000041 | Yes | H17 | A Project name with information 52 | Replacement | Replacement | 2022.7 | 2025 |  | Staion Name | L-206 | 125.25 | 126.25 |  | A City 52 | County 52 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
53 | Jane Smith | Assigned | Paul Smith | A name 3 | Some Name 2 |  | Contractor 2 |  |  | D-1234C | 740000042 | Yes | H16 | A Project name with information 53 | Replacement | Replacement | 2022.5 | 2025 | 2025-02-22 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 53 | County 53 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
54 | Jane Smith | Assigned | Paul Smith | A name 4 | Some Name 3 |  | Contractor 3 |  |  | D-1234C | 740000043 | Yes | H17 | A Project name with information 54 | Replacement | Replacement | 2022.3 | 2025 | 2025-02-23 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 54 | County 54 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
55 | Jane Smith | Assigned | Joe Smith | A name 3 | Some Name 2 |  | Contractor 2 |  |  | T-1245 | 740000044 | No | 759 | A Project name with information 55 | Replacement | Replacement | 2022.1 | 2025 | 2025-02-24 | Staion Name | L-300A | 125.25 | 126.25 |  | A City 55 | County 55 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
56 | Sauer, Shaun | Assigned | Paul Smith | A name 4 | Some Name 3 |  | Contractor 3 |  |  | D-1234C | 740000045 | Yes | H18 | A Project name with information 56 | Replacement | Replacement | 2021.8571 | 2025 | 2025-02-25 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 56 | County 56 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
57 | Sauer, Shaun | Assigned | Joe Smith | A name 3 | Some Name 2 |  | Contractor 2 |  |  | T-1243 | 740000046 | No | 757 | A Project name with information 57 | Replacement | Replacement | 2021.6486 | 2025 | 2025-02-26 | Staion Name | L-300A | 125.25 | 126.25 |  | A City 57 | County 57 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
58 | Sauer, Shaun | Assigned | Janney Red | A name 3 | Some Name 2 |  | Contractor 4 |  |  | D-1234B | 740000047 | Yes | H17 | A Project name with information 58 | Replacement | Replacement | 2021.44 | 2025 |  | Staion Name | L-205 | 125.25 | 126.25 |  | A City 58 | County 58 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
59 | Sauer, Shaun | Assigned | Paul Smith | A name 3 | Some Name 2 |  | Contractor 2 |  |  | D-1234C | 740000048 | Yes | H16 | A Project name with information 59 | Replacement | Replacement | 2021.2314 | 2025 | 2025-02-28 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 59 | County 59 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
60 | Sauer, Shaun | Assigned | Paul Smith | A name 4 | Some Name 3 |  | Contractor 3 |  |  | D-1234C | 740000049 | Yes | H17 | A Project name with information 60 | Replacement | Replacement | 2021.0229 | 2025 | 2025-03-01 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 60 | County 60 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
61 | Sauer, Shaun | Assigned | Joe Smith | A name 3 | Some Name 2 |  | Contractor 2 |  |  | T-1244 | 740000050 | No | 758 | A Project name with information 61 | Replacement | Replacement | 2020.8143 | 2025 | 2025-03-02 | Staion Name | L-300A | 125.25 | 126.25 |  | A City 61 | County 61 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
62 | Sauer, Shaun | Assigned | Janney Red | A name 3 | Some Name 2 |  | Contractor 4 |  |  | D-1234B | 740000051 | Yes | H17 | A Project name with information 62 | Replacement | Replacement | 2020.6057 | 2025 |  | Staion Name | L-206 | 125.25 | 126.25 |  | A City 62 | County 62 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
63 | Sauer, Shaun | Assigned | Paul Smith | A name 3 | Some Name 2 |  | Contractor 2 |  |  | D-1234C | 740000052 | Yes | H16 | A Project name with information 63 | Replacement | Replacement | 2020.3971 | 2025 | 2025-03-04 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 63 | County 63 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
64 | Sauer, Shaun | Assigned | Paul Smith | A name 4 | Some Name 3 |  | Contractor 3 |  |  | D-1234C | 740000053 | Yes | H17 | A Project name with information 64 | Replacement | Replacement | 2020.1886 | 2025 | 2025-03-05 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 64 | County 64 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
65 | Sauer, Shaun | Assigned | Joe Smith | A name 3 | Some Name 2 |  | Contractor 2 |  |  | T-1245 | 740000054 | No | 759 | A Project name with information 65 | Replacement | Replacement | 2019.98 | 2025 | 2025-03-06 | Staion Name | L-300A | 125.25 | 126.25 |  | A City 65 | County 65 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
66 | Jane Smith | Assigned | Janney Red | A name 3 | Some Name 2 |  | Contractor 4 |  |  | D-1234B | 740000055 | Yes | H17 | A Project name with information 66 | Replacement | Replacement | 2019.7714 | 2025 |  | Staion Name | L-207 | 125.25 | 126.25 |  | A City 66 | County 66 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
67 | Jane Smith | Assigned | Paul Smith | A name 3 | Some Name 2 |  | Contractor 2 |  |  | D-1234C | 740000056 | Yes | H16 | A Project name with information 67 | Replacement | Replacement | 2019.5629 | 2025 | 2025-03-08 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 67 | County 67 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
68 | Jane Smith | Assigned | Paul Smith | A name 4 | Some Name 3 |  | Contractor 3 |  |  | D-1234C | 740000057 | Yes | H17 | A Project name with information 68 | Replacement | Replacement | 2019.3543 | 2025 | 2025-03-09 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 68 | County 68 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
69 | Jane Smith | Assigned | Joe Smith | A name 3 | Some Name 2 |  | Contractor 2 |  |  | T-1246 | 740000058 | No | 760 | A Project name with information 69 | Replacement | Replacement | 2019.1457 | 2025 | 2025-03-10 | Staion Name | L-300A | 125.25 | 126.25 |  | A City 69 | County 69 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
70 | Jane Smith | Assigned | Paul Smith | A name 4 | Some Name 3 |  | Contractor 3 |  |  | D-1234C | 740000059 | Yes | H19 | A Project name with information 70 | Replacement | Replacement | 2018.9371 | 2025 | 2025-03-11 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 70 | County 70 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
71 | Jane Smith | Assigned | Joe Smith | A name 3 | Some Name 2 |  | Contractor 2 |  |  | T-1244 | 740000060 | No | 758 | A Project name with information 71 | Replacement | Replacement | 2018.7286 | 2025 | 2025-03-12 | Staion Name | L-300A | 125.25 | 126.25 |  | A City 71 | County 71 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
72 | Jane Smith | Assigned | Janney Red | A name 3 | Some Name 2 |  | Contractor 4 |  |  | D-1234B | 740000061 | Yes | H17 | A Project name with information 72 | Replacement | Replacement | 2018.52 | 2025 |  | Staion Name | L-206 | 125.25 | 126.25 |  | A City 72 | County 72 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
73 | Sauer, Shaun | Assigned | Paul Smith | A name 3 | Some Name 2 |  | Contractor 2 |  |  | D-1234C | 740000062 | Yes | H16 | A Project name with information 73 | Replacement | Replacement | 2018.3114 | 2025 | 2025-03-14 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 73 | County 73 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
74 | Sauer, Shaun | Assigned | Paul Smith | A name 4 | Some Name 3 |  | Contractor 3 |  |  | D-1234C | 740000063 | Yes | H17 | A Project name with information 74 | Replacement | Replacement | 2018.1029 | 2025 | 2025-03-15 | Staion Name | L-300B | 125.25 | 126.25 |  | A City 74 | County 74 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
75 | Sauer, Shaun | Assigned | Joe Smith | A name 3 | Some Name 2 |  | Contractor 2 |  |  | T-1245 | 740000064 | No | 759 | A Project name with information 75 | Replacement | Replacement | 2017.8943 | 2025 | 2025-03-16 | Staion Name | L-300A | 125.25 | 126.25 |  | A City 75 | County 75 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31
76 | Sauer, Shaun | Assigned | Janney Red | A name 3 | Some Name 2 |  | Contractor 4 |  |  | D-1234B | 740000065 | Yes | H17 | A Project name with information 76 | Replacement | Replacement | 2017.6857 | 2025 |  | Staion Name | L-207 | 125.25 | 126.25 |  | A City 76 | County 76 | 2025-10-02 |  | 2025-11-01 | 2025-12-02 | 2025-02-02 | 2026-01-26 | 2026-01-27 |  |  | 2025-11-01 | 2025-12-01 | 2025-12-12 | 338186 | 2025-12-30 | 2026-01-01 |  | 2026-04-02 | 2026-04-10 |  | 2026-12-31